## Test Summary Report
Test Summary report
| Test Cycle |  | System Testing | Date of the report | 17-08-2025 | APP. Name | OrangeHRM
|  |  |  | time of the report | 16:38 | QA testers | Project QA Team
| EXECUTED | PASSED |  |  |  |  | 203
|  | FAILED |  |  |  |  | 22
|  | TOTAL | [5 empty] | 225
| PENDING | [6 empty] | 0
| IN PROGRESS | [6 empty] | 0
| BLOCKED | [6 empty] | 0
| (Sub-Total) TEST PLANNED | [6 empty] | 0
| (PENDING. INPROGRESS. BLOCKED. TEST EXECUTED) | [6 empty] | 225
REQ-ID | Functions |  | Description | %TC.S Executed | %TC.S Passed |  | TC.S Failed | Priority
REQ-AUTH-01 | Authentication | Valid User Credentials Authentication |  | 100% | 100% |  | 0 | High
REQ-AUTH-02 | Authentication | Invalid Credentials Error Handling |  | 100% | 100% |  | 0 | High
REQ-RBAC-01 | Authentication | Administrator Full System Access |  | 100% | 100% |  | 0 | High
REQ-RBAC-02 | Authentication | : User Personal Data Access Control |  | 100% | 100% |  | 0 | High
REQ-RBAC-03 | Authentication | Sensitive Field Edit Restrictions |  | 100% | 100% |  | 0 | High
REQ-SECURITY-01 | Unfunctional | loading and usability |  | 100% | 0% |  | 100% | High
REQ-UM-001 | User Module | The system shall display the personal Details screen upon the user’s first successful login and allow the user to view and edit their personal information. |  | 100% | 60% |  | 40% | High
REQ-UM-002 | User Module | The system shall restrict the user’s ability to modify certain fields in the Personal Details screen, including Employee ID, Driver License Number, and Date of Birth |  | 100% | 100% |  | 0 | High
REQ-UM-003 | User Module | The system shall allow the user to upload a photograph to the Personal Details screen, with a maximum file size of 1 MB and in one of the following formats: JPG, PNG, or GIF. |  | 100% | 100% |  | 0 | Medium
REQ-UM-004 | User Module | The system shall allow users to edit their contact information in the Personal Details screen, including Country, Street 1, Street 2, City/Town, State/Province, ZIP Code, Home Telephone, Mobile, Work Telephone, Work Email, and Other Email. |  | 100% | 70% |  | 30% | High
REQ-UM-005 | User Module | The system shall allow users to add, edit, and delete one or more emergency contacts, and upload appropriate attachments in the Emergency Contacts screen. |  | 100% | 100% |  | 0 | High
REQ-UM-006 | User Module | The system shall allow users to add, edit, and delete one or more dependents, and upload appropriate attachments in the Dependents screen |  | 100% | 85% |  | 15% | High
REQ-UM-007 | User Module | The system shall allow users to add, delete, and enter comments for one or more immigration documents (Passport/Visa) along with their related details, and upload attachments associated with each immigration document |  | 100% | 90% |  | 10% | High
REQ-UM-008 | User Module | The system shall restrict the User from editing any fields in the Job Details screen, allowing the user to only view pre-defined job details. |  | 100% | 100% |  | 0 | High
REQ-UM-009 | User Module | The system shall hide salary information from the User, and restrict the user from editing any salary details fields |  | 100% | 100% |  | 0 | High
REQ-UM-010 | User Module | The system shall restrict the User from editing the "Report To" information and allow the user to only view the list of assigned supervisors or subordinates, including any attachments. |  | 100% | 100% |  | 0 | High
REQ-UM-011 | User Module | The system shall allow users to add, edit, and delete one or multiple entries in the Work Experience section. Deletion may be performed by selecting single or multiple checkboxes and clicking “Delete. |  | 80% | 100 |  | 20% | High
REQ-UM-012 | User Module | The system shall allow users to add, edit, and delete one or multiple entries in the Education section. Deletion may be performed by selecting single or multiple checkboxes and clicking “Delete. |  | 100 | 50% |  | 45% | High
REQ-UM-013 | User Module | The system shall allow users to add, edit, and delete one or multiple entries in the Skills section. Deletion may be performed by selecting single or multiple checkboxes and clicking “Delete |  | 100% | 100% |  | 100% | High
REQ-UM-014 | User Module | : The system shall allow users to add multiple languages of competency with their corresponding competency levels. The system shall display each saved language entry in the Language list. The system shall allow users to delete one or multiple language entries by selecting the corresponding checkboxes and clicking “Delete |  | 100% | 100% |  | 100% | High
REQ-UM-015 | User Module | The system shall allow users to add multiple license entries by entering the required details and clicking “Save.” The system shall display each saved license in the License list. The system shall allow users to delete one or multiple license entries by selecting the corresponding checkboxes and clicking “Delete |  | 100% | 80% |  | 20% | High
REQ-UM-016 | User Module | The system shall allow users to attach multiple supporting documents related to their qualifications. Each document shall not exceed 1 megabyte in size. The system shall display each uploaded document in the attachment list. The system shall allow users to delete one or multiple attachments by selecting the corresponding checkboxes and clicking “Delete |  | 100% | 100% |  | 100% | High
REQ-UM-017 | User Module | The system shall allow users to add, view, edit, and delete single or multiple membership records, and to upload supporting attachments for each membership |  | 100% | 100% |  | 100% | High
REQ-ADMIN-1 | Admin Module | The system shall allow Admins to fully manage users and roles, including adding/editing/deleting accounts, assigning access levels, and enabling/disabling users. |  | 100% | 100% |  | 100% | High
REQ-ADMIN-2 | Admin Module | The system shall allow the Admin to manage job titles (add, edit, delete, and list multiple titles) and to define pay grades by setting salary ranges, step increases, and currencies |  | 100% | 100% |  | 100% | High
REQ-ADMIN-3 | Admin Module | The system shall allow the Admin to define the status of employment employees (add, edit, delete employment status) |  | 100% | 100% |  | 100% | High
REQ-ADMIN-4 | Admin Module | The system shall allow the Admin to create job categories (add) or edit/delete the job categories |  | 100% | 100% |  | 100% | High
REQ-ADMIN-5 | Admin Module | The system shall allow the Admin to define work shifts by adding or editing or deleting them |  | 100% | 100% |  | 100% | High
REQ-ADMIN-6 | Admin Module | The system shall allow the admin to edit the general information about the organization or the company |  | 100% | 100% |  | 100% | High
REQ-ADMIN-7 | Admin Module | The system shall allow the admin to add details of sites and branches of the company or editing or deleting them also the Admin can search for a specific location |  | 100% | 100% |  | 100% | High
REQ-ADMIN-8 | Admin Module | The system shall allow the admin to define the structure of the organization by adding units and sub units or editing or deleting them |  | 100% | 100% |  | 100% | High
REQ-ADMIN-9 | Admin Module | The system shall allow the admin to define all informations with regards to employees qualifications by (add, edit, delete) for these qualifications like (skills, education, license, languages, memberships) |  | 100% | 100% |  | 100% | High

## Defect Distribution report
OrangeHRM. Website
Bug ID | Bug Title | Priority | Severity | Status | Assigned to
B-01 | First login -no personal details displayed | Low | Severity 4 | Deferred | Not Assigned
B-02 | personal information saving with blank field | High | Severity 2 | New | Not Assigned
B-03 | state/provice not switching | Medium | Severity 3 | New | Not Assigned
B-04 | city/town field bug | High | Severity 3 | New | Not Assigned
B-05 | Zip/code field bug | High | Severity 3 | New | Not Assigned
B-06 | Date of Birth Field Bug | High | Severity 2 | Open | Not Assigned
B-07 | Name field bug | High | Severity 2 | New | Not Assigned
B-08 | Issue date field bug | High | Severity 2 | Open | Not Assigned
B-09 | company name field bug | Medium | Severity 3 | New | Not Assigned
B-10 | Job title field bug | Medium | Severity 3 | New | Not Assigned
B-11 | from/To work experience Date Bug | High | Severity 2 | Open | Not Assigned
B-12 | Deleting an education entry bug | High | Severity 2 | Open | Not Assigned
B-13 | Deleting multiple education entry | Medium | Severity 3 | Open | Not Assigned
B-14 | The major specification field bug | High | Severity 2 | New | Not Assigned
B-15 | The institution field bug | High | Severity 3 | New | Not Assigned
B-16 | The year field bug | High | Severity 2 | Non-Producable | Not Assigned
B-17 | The year field format bug | High | Severity 2 | New | Not Assigned
B-18 | GPA/Score field bug | High | Severity 2 | Open | Not Assigned
B-19 | Start/End date field bug | Medium | Severity 3 | New | Not Assigned
B-20 | Licence Number field bug | High | Severity 2 | Open | Not Assigned
B-21 | The issue/Expiry date field bug | High | Severity 2 | Open | Not Assigned
B-22 | Loading of the website is slow | High | Severity 3 | Open | Not Assigned
DEFECT DISTRIBUTION REPORT
|  | # | PRIORITY
|  | High | 16
|  | Medium | 5
|  | Low | 1
|  | Total | 22
|  | # | SEVERITY
|  | Severity 1 | 0
|  | Severity2 | 12
|  | Severity 3 | 9
|  | Severity 4 | 1
|  | Priority/severity | Status | Number
|  | High - Severity 2 | Open | 9
|  | High - Severity 2 | non-producable | 1
|  | High - Severity 2 | New | 4
|  | High - Severity 3 | Open | 1
|  | Low - Severity 4 | Deferred | 1
|  | Medium- Severity 3 | New | 4
|  | Medium- Severity 3 | Open | 1
|  | High - Severity 3 | New | 1